Clinical Research Strategic Delivery Standards  |  Part III: The Strategic Partnership Toolkit

d. Study Review

4. Structured Process Improvement Cycle

The post-study review is a collaborative learning session, not a performance evaluation. It compares expectations with outcomes and identifies practical improvements for future studies.

For long studies, a structured mid-study review at 25 or 50 percent enrollment allows for improvements while the study is still running.

Shaded cells are for completion.

| Study |  |
| --- | --- |
| Sponsor |  |
| MCRC |  |
| Date |  |
| Review | ☐ Post-study review ☐ Mid-study review at 25 percent enrollment ☐ Mid-study review at 50 percent enrollment |

| Review area | What it covers | Expectations | Outcomes |
| --- | --- | --- | --- |
| Feasibility planning | Accuracy of patient population estimates, disease burden, recruitment assumptions, timelines, competitive landscape including competing trials and new product launches, budget expectations |  |  |
| Trial administration | Communication burden, vendor management including the case for a single portal with single sign-on, duplicate training requirements |  |  |
| Recruitment | Forecast versus actual enrollment and the reasons for over- or under-performance |  |  |
| Screen failures | Primary causes: eligibility issues, patient misunderstanding, protocol complexity |  |  |
| Protocol design | Procedures that created operational burden for sites or patients without adding scientific value |  |  |
| Study startup | Timelines, contracting, IRB approvals, vendor-related bottlenecks |  |  |
| Data quality | Protocol deviations and query trends |  |  |
| Payments | Site reimbursement timelines, sponsor payment processes, patient stipends |  |  |
| Patient retention | Dropout rates, timing, underlying reasons |  |  |
| Successes | Processes, tools, vendors, or approaches worth standardizing across future studies |  |  |

Each review produces no more than five actionable recommendations, each with an assigned owner, and a commitment to apply the lessons in future studies.

|  | Recommendation | Assigned owner |
| --- | --- | --- |
| 1 |  |  |
| 2 |  |  |
| 3 |  |  |
| 4 |  |  |
| 5 |  |  |

|  | Name | Signature | Date |
| --- | --- | --- | --- |
| Sponsor |  |  |  |
| MCRC |  |  |  |